## First Two Weeks
Timing | Weekday | Date | Time | Duration | Activity | Type | Expected Outcome | Sponsor | Server/Network Administrators | Application Owners | Metrics Owners | Azure Administrators | Database Administrators | Security Administrators | ID, Access Management
Day1 | Wednesday | 2021-03-10 | 1230 EST | 30 Min | Kick-off meeting | Data Gathering | Understand expectations for the engagement, discuss current Azure status, discuss application targets, and identify points of contact for the engagement | x | x | x | x | x | x | x | x
Day2 | Thursday | 2021-03-11 | 1230 EST | 30 mins | Movere Pre-Deployment Session | Planning | Coordinate with Azure Subscription contact to create Movere Project. It is recommended for personnel setting up the project to have Contributor Permissions for ease of install. If Azure tenant not ready, we can discuss current actions, roadblocks, and way ahead for manual Server Assessment | x | x |  |  | x |  | x | x
Day2 | Thursday | 2021-03-11 | 1300 EST | 30 mins | Application 1 Discovery/Interview | Data Gathering | Understand scope of application, VM sizes, server specifications, and usage to enable Azure estimates (See App Rat Initial Questions tab) | x | x | x | x |  | x | x | x
Day2 | Thursday | 2021-03-11 | 1330 EST | 30 mins | Application 2 Discovery/Interview | Data Gathering | Understand scope of application, VM sizes, server specifications, and usage to enable Azure estimates (See App Rat Initial Questions tab) | x | x | x | x |  | x | x | x
Day3 | Friday | 2021-03-12 | NA | NA | NA
Day4 | Tuesday | 2021-03-16 | 1300 EST | 30 mins | Application 3 Discovery/Interview | Data Gathering | Understand scope of application, VM sizes, server specifications, and usage to enable Azure estimates (See App Rat Initial Questions tab) | x | x | x | x |  | x | x | x
Day4 | Tuesday | 2021-03-16 | 1330 EST | 30 mins | Application 4 Discovery/Interview | Data Gathering | Understand scope of application, VM sizes, server specifications, and usage to enable Azure estimates (See App Rat Initial Questions tab) | x | x | x | x |  | x | x | x
Day4 | Tuesday | 2021-03-16 | 1400 EST | 30 mins | Application 5 Discovery/Interview | Data Gathering | Understand scope of application, VM sizes, server specifications, and usage to enable Azure estimates (See App Rat Initial Questions tab) | x | x | x | x |  | x | x | x
Day5 | Tuesday | 2021-03-16 | NA | NA | NA
Day6 | Wednesday | 2021-03-17 | 1000 EST | 30 mins | Movere status. Placeholder for Movere project review | Planning | Movere status update, Azure Subscription/Landing Zone update, and answer any questions the customer or CloudFit may have | x |  |  |  | x
Day6 | Wednesday | 2021-03-17 | 1030 EST | 30 mins | Follow up Application Rationalization Session for App 1 | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day6 | Wednesday | 2021-03-17 | 1100 EST | 30 mins | Follow up Application Rationalization Session for App 2 | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day7 | Thursday | 2021-03-18 | NA | NA | NA
Day8 | Friday | 2021-03-19 | 1000 EST | 30 mins | Follow up Application Rationalization Session for App 3 | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day8 | Friday | 2021-03-19 | 1030 EST | 30 mins | Follow up Application Rationalization Session for App 4 | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day8 | Friday | 2021-03-19 | 1230 EST | 30 mins | Follow up Application Rationalization Session for App 5 | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day9 | Monday | 2021-03-22 | 1000 EST | 30 mins | Follow up Application Rationalization Session | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day9 | Monday | 2021-03-22 | 1030 EST | 30 mins | Follow up Application Rationalization Session | Data Gathering | Verify information received and allow CloudFit and customer to ask follow up questions for the application rationalization | x | x | x | x |  | optional | optional | optional
Day9 | Monday | 2021-03-22 | 1100 EST | 30 mins | Movere status. Placeholder for Movere project review | Planning | Movere status update, Azure Subscription/Landing Zone update, and answer any questions the customer or CloudFit may have | x |  |  |  | x

## App Rat Initial Questions
Application Rationalization Discovery Questions
Only a starting point, not the end-all-be-all
General Assessment Questions
1. Who are the decision makers within your organization for Cloud Strategy? | i
2. Who are the decision makers within your organization for Cloud Implementation?
3. Who are the application owners for this assessment and will they be available for the next four weeks?
Azure Subscription General Questions
1. Is your Azure subscription set up and functional for all of your environments (IL4, IL5, IL6)?
2. Do you (or someone in your organization) have subscription Owner/Contributor permissions?
3. Are you new to Azure?
4. What level of experience do you have working within Azure?
Cloud Environment
1. What is your expectation/current plan for connecting to remote VMs?
a. This would be either RDP, SSH, an express route, etc
2. Are there any specific requirements and/or plans for Identity Management in the cloud? (Authentication and Authorization)
3. Are there any specific requirements and/or plans for managing VMs in the cloud?
4. Will there be an Express Route in place for your environment?
5. Where will this application “live”?
a. Government Commerical Cloud (GCC)?
b. GCC High?
c. Impact Level (IL) 5?
d. IL6?
Application VMs
1. Are there any existing documentation and/or architecture diagrams available for the application being migrated?
a. Are there multiple environments for this? (Dev, QA, Test, Prod, etc.)
2. What is the hardware/resource specifications for servers in use for this application?
a. CPU
b. Memory
c. Storage
i. Local (VDI, physical, file, etc.)
ii. Remote (Redis, gluster, iscsi, etc.)
3. What monitoring and logging tools/solutions are currently in place?
a. What metrics are available for the application?
i. CPU Usage
ii. Memory Usage
iii. Storage Utilization
iv. Application specific metrics
4. What is the existing process in place for VM patches or upgrades?
5. Are there currently any backup or disaster recovery strategies in place?
a. Backup schedule
b. Hot/warm/cold site
6. What is the uptime requirement for this application?
a. Is this application required to be running 24/7 or only when a specific action needs to be performed?
7. Are there currently any load balancers or firewalls in use in front of the application? If so, please give some detailed information about current setup and schemes. (ie: round robin)
8. Is this application secured with TLS? (self-signed, CA-signed, etc.)
9. What type of authentication/authorization is currently in use for this application?
10. How many users currently use this application regularly?
a. Is there a variety of user roles, or just a single role?
11. What form of method is currently in use for secret storage (admin passwords, TLS certs, etc)? (software or physical)
12. Are there any security/auditing currently in use?
Application Databases
1. Are there any existing documentation and/or architecture diagrams available for the application databases being migrated?
a. Is there a dedicated database per environment listed above?
b. Clustered, multiple Databases (dbs), etc?
2. What is the hardware/resource specifications for databases in use for this application?
a. CPU
b. Memory
c. Storage
i. Local (VDI, physical, file, etc.)
ii. Remote (gluster, iscsi, etc.)
3. What monitoring and logging tools/solutions are currently in place?
a. What metrics are available for the application?
i. CPU Usage
ii. Memory Usage
iii. Storage Utilization
iv. IOPS (input/output operations per second)
4. Are there currently any backup or disaster recovery strategies in place?
a. Backup schedule
b. Hot/warm/cold site
Proprietary Applications (may not be applicable)
1. What development stack is currently in use? (.NET framework vs. Core, versions, etc)
2. Is the application currently containerized or are there plans for it to be containerized soon?
3. Are there any necessary dependencies? (other applications, private repos, etc)
4. Where is the source code currently stored?
5. What development pipelines do you currently have in place?
a. Pull requests
b. Testing processes
c. Release process
6. Is there any existing feature/issue tracking in place?
Information Assurance (IA) Considerations
1. Do you have an Azure Cloud Access Point created (CAP) if this application lives in IL5?
2. Does your IA Representative have the Authority to Operate (ATO) paperwork available for the production applications being rationalized?
3. For any IL6 workloads, is your Azure enclave accredited?

## Application Sizing Definitions
*Application Sizing | Simple | Medium | Complex
| Few or no dependencies on other libraries. | Well-documented dependencies on other libraries or platforms. | Design and implement cloud-native architectures and frameworks for utmost modernization and defensibility.
| Relative low effort to install, config, and/or build. | Customization and configuration of a pre-determined number of sample workloads. | Decomposition, design, and deployment of all associated critical workloads.
| Smaller memory footprint. | Larger memory footprint. | Architect memory footprint to take advantage of cloud elastic storage from inception.
| Smaller interface. | Larger interface. | Complex interfaces, potentially including foreign national use cases or sovereign domains.
| Single central identity model. | Advanced identity model with set number of use cases and constraints (MFA, CAC, etc) | Partner identity models with security enclave boundaries and governance controls.
| Limited ingress/egress with on-prem dependencies. | Ingress/egress architecture includes network /firewall, port, or conditional access policies for sample workloads predefined. | Azure native or 3rd party CSSP tooling.
| Smaller absolute amount of code. | More advanced codebase. | Custom code development.
| Single rationalized databases in third normal form. | More advanced database structures with some normalization or schema design. | Expansive database structures natively realized in the cloud and enabled by PaaS and microservices.